## Summary
ProSteel Shopify Migration Control
Control | Value
Verified website products | 72
Existing Shopify products mapped | 13
Products to create as drafts | 59
Existing price corrections required | 13
Existing title corrections required | 1
Migration rules
1. Preserve existing Shopify product IDs and available quantities.
2. Use the verified website/brochure price as the approved storefront price.
3. Assign a unique model-based SKU before any inventory import.
4. Create missing products as drafts until media, specifications, and collection mapping pass QA.
5. Build and test only in an unpublished theme; never overwrite or publish the live Canyon theme during migration.

## Product Mapping
Website Slug | Product Name | Model | Collection | Category | Approved Price | Shopify Product ID | Shopify Current Title | Shopify Current Price | Available | Current SKU | Desired SKU | Migration Status | Price Difference
pse-20-33-2 | 2-Cylinder Gas Cage | PSE 20-33-2 | gas-cage | Propane & BBQ | 501 | 9193566240906 | PSE 20-33-2 | 501.62 | 5 |  | PSE-20-33-2 | Existing - price correction | 0.62
pse-20-33-4 | 4-Cylinder Gas Cage | PSE 20-33-4 | gas-cage | Propane & BBQ | 550 | 9193566142602 | PSE 20-33-4 | 548.49 | 7 |  | PSE-20-33-4 | Existing - price correction | -1.51
pse-20-33-6 | 6-Cylinder Gas Cage | PSE 20-33-6 | gas-cage | Propane & BBQ | 635 | 9193566175370 | PSE 20-33-6 | 633.41 | 9 |  | PSE-20-33-6 | Existing - price correction | -1.59
pse-100-20-8-18 | Dual-Capacity Cylinder Cage | PSE 100-20-8-18 | gas-cage | Propane & BBQ | 1485 | 9193566208138 | PSE 100-20-8-18 | 1484.28 | 4 |  | PSE-100-20-8-18 | Existing - price correction | -0.72
pse-33-12 | 12-Cylinder 33 lb Cage | PSE 33-12 | gas-cage | Forklift | 1008 | 9193578201226 | PSE 33-12 | 1008.93 | 10 |  | PSE-33-12 | Existing - price correction | 0.93
pse-20-24 | 24-Cylinder BBQ Cage | PSE 20-24 | gas-cage | Propane & BBQ | 1499 | 9193578397834 | PSE 20-24 | 1499.44 | 3 |  | PSE-20-24 | Existing - price correction | 0.44
pse-20-12 | 12-Cylinder BBQ Cage | PSE 20-12 | gas-cage | Propane & BBQ | 890 | 9193578594442 | PSE 20-12 | 891.46 | 8 |  | PSE-20-12 | Existing - price correction | 1.46
pse-33-18 | 18-Cylinder Forklift Cage | PSE 33-18 | gas-cage | Forklift | 1249 | 9193578889354 | PSE 33-12 | 1249.12 | 4 |  | PSE-33-18 | Existing - title and price correction | 0.12
pse-33-8 | 8-Cylinder Forklift Cage | PSE 33-8 | gas-cage | Forklift | 1042 | 9193606971530 | PSE 33-8 | 1042.74 | 6 |  | PSE-33-8 | Existing - price correction | 0.74
pse-20-18 | 18-Cylinder BBQ Cage | PSE 20-18 | gas-cage | Propane & BBQ | 1310 | 9193579446410 | PSE 20-18 | 1309.7 | 11 |  | PSE-20-18 | Existing - price correction | -0.3
pse-33-147-8-4 | Combination Forklift & Welding Cage | PSE 33-147-8-4 | gas-cage | Combination | 1567 | 9193579872394 | PSE 33-147-8-4 | 1567.33 | 2 |  | PSE-33-147-8-4 | Existing - price correction | 0.33
pse-147-7-8 | 8-Cylinder Welding Cage | PSE 147.7-8 | gas-cage | Welding | 1520 | [5 empty] | PSE-147-7-8 | Create as draft
pse-147-7-20 | 20-Cylinder Welding Cage | PSE 147.7-20 | gas-cage | Welding | 1955 | [5 empty] | PSE-147-7-20 | Create as draft
pse-147-7-16 | 16-Cylinder Welding Cage | PSE 147.7-16 | gas-cage | Welding | 1350 | [5 empty] | PSE-147-7-16 | Create as draft
pse-al-147-7-16 | Aluminum Oxygen Cylinder Cage | PSE AL 147.7-16 | gas-cage | Medical Gas | 1750 | [5 empty] | PSE-AL-147-7-16 | Create as draft
pse-fwb | Firewood Bundle Cage | PSE FWB | gas-cage | Specialty Carrier | 1440 | 9193580757130 | PSE FWB | 1141.9 | 3 |  | PSE-FWB | Existing - price correction | -298.1
model-420-1 | Forklift / Crane Bottle Carrier | 420-1 | gas-cage | Specialty Carrier | 853 | 9193619980426 | PSE 420-1 | 852.91 | 4 |  | PSE-420-1 | Existing - price correction | -0.09
economy-a-frame | Economy A-Frame | Economy A-Frame | material-rack | A-Frame | 550 | [5 empty] | PSE-ECONOMY-A-FRAME | Create as draft
single-sided-a-frame | Single-Sided A-Frame | Single-Sided A-Frame | material-rack | A-Frame | 490 | [5 empty] | PSE-SINGLE-SIDED-A-FRAME | Create as draft
heavy-duty-a-frame | Heavy Duty A-Frame | Heavy Duty A-Frame | material-rack | A-Frame | 1450 | [5 empty] | PSE-HEAVY-DUTY-A-FRAME | Create as draft
double-sided-transport-rack | Double-Sided Transport & Storage Rack | Double-Sided Transport Rack | material-rack | Transport Rack | 1690 | [5 empty] | PSE-DOUBLE-SIDED-TRANSPORT-RACK | Create as draft
modular-transport-rack | Metal Modular Transport Rack | Modular Transport Rack | material-rack | Transport Rack | 1250 | [5 empty] | PSE-MODULAR-TRANSPORT-RACK | Create as draft
mobile-a-frame | Mobile A-Frame Transport Rack | Mobile A-Frame | material-rack | Mobile Rack | 1800 | [5 empty] | PSE-MOBILE-A-FRAME | Create as draft
mobile-l-frame | Mobile L-Frame Transport Rack | Mobile L-Frame | material-rack | Mobile Rack | 1345 | [5 empty] | PSE-MOBILE-L-FRAME | Create as draft
stone-fabrication-a-frame | Stone Fabrication A-Frame | Double-Sided Stone A-Frame | material-rack | A-Frame | 475 | [5 empty] | PSE-DOUBLE-SIDED-STONE-A-FRAME | Create as draft
solo-shelf-rack | Solo Shelf Rack | Solo Shelf Rack - 2 Piece | material-rack | Single-Sided Rack | 1550 | [5 empty] | PSE-SOLO-SHELF-RACK-2-PIECE | Create as draft
one-side-l-frame | One-Side L-Frame for Glass | One-Side L-Frame | material-rack | Single-Sided Rack | 1350 | [5 empty] | PSE-ONE-SIDE-L-FRAME | Create as draft
heavy-duty-double-sided-a-frame | Heavy Duty Double-Sided A-Frame | Heavy Duty Double-Sided A-Frame | material-rack | A-Frame | 1450 | [5 empty] | PSE-HEAVY-DUTY-DOUBLE-SIDED-A-FRAME | Create as draft
multi-purpose-slab-rack | Multi-Purpose Slab Rack | PSE PS10 | material-rack | Slab Rack | 2850 | [5 empty] | PSE-PS10 | Create as draft
heavy-duty-bundle-slab-rack | Heavy-Duty Bundle Slab Rack With Rubber Cap | PSE PS10 | material-rack | Slab Rack | 3400 | [5 empty] | PSE-PS10 | Create as draft
one-side-frame-narrow-warehouse | One Side Frame for Narrow Warehouse | One Side Frame | material-rack | Single-Sided Rack | 925 | [5 empty] | PSE-ONE-SIDE-FRAME | Create as draft
heavy-duty-bundle-slab-rack-standard | Heavy-Duty Bundle Slab Rack | PSE PS10 | material-rack | Slab Rack | 2850 | [5 empty] | PSE-PS10 | Create as draft
heavy-duty-mobile-transport-frame | Heavy Duty Mobile Transport Frame | Heavy Duty Mobile Transport Frame | industrial-table | Mobile Transport Frame | 1025 | [5 empty] | PSE-HEAVY-DUTY-MOBILE-TRANSPORT-FRAME | Create as draft
three-tier-triple-stacker-table | 3-Tier Triple Stacker Table | 3-Tier Triple Stacker Table | industrial-table | Stacker Table | 810 | [5 empty] | PSE-3-TIER-TRIPLE-STACKER-TABLE | Create as draft
heavy-duty-industrial-platform-cart | Heavy Duty Industrial Platform Cart | Heavy Duty Industrial Platform Cart | industrial-table | Platform Cart | 675 | [5 empty] | PSE-HEAVY-DUTY-INDUSTRIAL-PLATFORM-CART | Create as draft
garment-production-utility-cart | Garment Production Utility Cart | Garment Production Utility Cart | industrial-table | Utility Cart | 790 | [5 empty] | PSE-GARMENT-PRODUCTION-UTILITY-CART | Create as draft
heavy-duty-six-wheel-work-table | Heavy-Duty 6-Wheel Work Table | Heavy-Duty 6-Wheel Work Table | industrial-table | Work Table | 1075 | [5 empty] | PSE-HEAVY-DUTY-6-WHEEL-WORK-TABLE | Create as draft
heavy-duty-steel-workbench | Heavy-Duty Steel Workbench | Heavy-Duty Steel Workbench | industrial-table | Workbench | 930 | [5 empty] | PSE-HEAVY-DUTY-STEEL-WORKBENCH | Create as draft
industrial-mobile-workbench | Industrial Mobile Workbench | Industrial Mobile Workbench | industrial-table | Workbench | 1350 | [5 empty] | PSE-INDUSTRIAL-MOBILE-WORKBENCH | Create as draft
three-tier-heavy-duty-mobile-assembly-workbench | 3-Tier Heavy-Duty Mobile Assembly Workbench | 3-Tier Mobile Assembly Workbench | industrial-table | Assembly Workbench | 1315 | [5 empty] | PSE-3-TIER-MOBILE-ASSEMBLY-WORKBENCH | Create as draft
large-heavy-duty-industrial-platform-cart | Large Size Heavy Duty Industrial Platform Cart | Large Industrial Platform Cart | industrial-table | Platform Cart | 1050 | [5 empty] | PSE-LARGE-INDUSTRIAL-PLATFORM-CART | Create as draft
mobile-glass-handling-table | Mobile Glass Handling Table | Mobile Glass Handling Table | industrial-table | Glass Handling Table | 990 | [5 empty] | PSE-MOBILE-GLASS-HANDLING-TABLE | Create as draft
heavy-duty-industrial-metal-top-platform-cart | Heavy Duty Industrial Metal Top Platform Cart | Metal Top Platform Cart | industrial-table | Platform Cart | 1025 | [5 empty] | PSE-METAL-TOP-PLATFORM-CART | Create as draft
mobile-electronics-workstation | Mobile Electronics Workstation | Mobile Electronics Workstation | industrial-table | Mobile Workstation | 990 | [5 empty] | PSE-MOBILE-ELECTRONICS-WORKSTATION | Create as draft
heavy-duty-two-tier-service-cart-stainless-steel | Heavy-Duty 2-Tier Service Cart | Stainless Steel 2-Tier Service Cart | industrial-table | Stainless Steel Cart | 980 | [5 empty] | PSE-STAINLESS-STEEL-2-TIER-SERVICE-CART | Create as draft
butchers-meat-cutting-table-stainless-steel | Butcher's Meat Cutting Table | Stainless Steel Meat Cutting Table | industrial-table | Stainless Steel Table | 1480 | [5 empty] | PSE-STAINLESS-STEEL-MEAT-CUTTING-TABLE | Create as draft
heavy-duty-16-ga-cutting-table | Heavy Duty 16 Ga. Cutting Table | 16 Ga. Cutting Table | industrial-table | Stainless Steel Table | 2050 | [5 empty] | PSE-16-GA-CUTTING-TABLE | Create as draft
commercial-pizza-prep-table | Commercial Pizza Prep Table | Commercial Pizza Prep Table | industrial-table | Stainless Steel Table | 2250 | [5 empty] | PSE-COMMERCIAL-PIZZA-PREP-TABLE | Create as draft
heavy-duty-bollard-bolt-down-4-dia-36 | Heavy Duty Bolt-Down Bollard - 4 in x 36 in | 4 in dia x 36 in H | warehouse-safety | Bollards | 145 | [5 empty] | PSE-4-IN-DIA-X-36-IN-H | Create as draft
heavy-duty-bollard-bolt-down-4-dia-42 | Heavy Duty Bolt-Down Bollard - 4 in x 42 in | 4 in dia x 42 in H | warehouse-safety | Bollards | 160 | [5 empty] | PSE-4-IN-DIA-X-42-IN-H | Create as draft
heavy-duty-bollard-bolt-down-4-dia-48 | Heavy Duty Bolt-Down Bollard - 4 in x 48 in | 4 in dia x 48 in H | warehouse-safety | Bollards | 175 | [5 empty] | PSE-4-IN-DIA-X-48-IN-H | Create as draft
heavy-duty-bollard-bolt-down-4-dia-60 | Heavy Duty Bolt-Down Bollard - 4 in x 60 in | 4 in dia x 60 in H | warehouse-safety | Bollards | 180 | [5 empty] | PSE-4-IN-DIA-X-60-IN-H | Create as draft
overhead-door-track-protector-48-in-ht | Overhead Door Track Protector - 48 in HT | 48 in HT / 9.86 x 6.58 in plate | warehouse-safety | Door Protection | 140 | [5 empty] | PSE-48-IN-HT-9-86-X-6-58-IN-PLATE | Create as draft
overhead-door-track-protector-36-in-ht | Overhead Door Track Protector - 36 in HT | 36 in HT / 9.86 x 6.58 in plate | warehouse-safety | Door Protection | 120 | [5 empty] | PSE-36-IN-HT-9-86-X-6-58-IN-PLATE | Create as draft
heavy-duty-mid-rail-machine-guard-24x18 | Heavy Duty Mid-Rail Machine Guard - 24 x 18 in | 24 x 18 in | warehouse-safety | Machine Guards | 370 | [5 empty] | PSE-24-X-18-IN | Create as draft
heavy-duty-mid-rail-machine-guard-26x18 | Heavy Duty Mid-Rail Machine Guard - 26 x 18 in | 26 x 18 in | warehouse-safety | Machine Guards | 450 | [5 empty] | PSE-26-X-18-IN | Create as draft
heavy-duty-mid-rail-machine-guard-24x42 | Heavy Duty Mid-Rail Machine Guard - 24 x 42 in | 24 x 42 in | warehouse-safety | Machine Guards | 500 | [5 empty] | PSE-24-X-42-IN | Create as draft
rack-protector-7x12-3ga | Rack Protector - 7 x 12 in, 3 Ga. | Fits 7 in post / 12 in H | warehouse-safety | Rack Protection | 55 | [5 empty] | PSE-FITS-7-IN-POST-12-IN-H | Create as draft
rack-protector-7x18-3ga | Rack Protector - 7 x 18 in, 3 Ga. | Fits 7 in post / 18 in H | warehouse-safety | Rack Protection | 75 | [5 empty] | PSE-FITS-7-IN-POST-18-IN-H | Create as draft
rack-protector-7x24-3ga | Rack Protector - 7 x 24 in, 3 Ga. | Fits 7 in post / 24 in H | warehouse-safety | Rack Protection | 90 | [5 empty] | PSE-FITS-7-IN-POST-24-IN-H | Create as draft
rack-protector-5x12-3ga | Rack Protector - 5 x 12 in, 3 Ga. | Fits 5 in post / 12 in H | warehouse-safety | Rack Protection | 45 | [5 empty] | PSE-FITS-5-IN-POST-12-IN-H | Create as draft
rack-protector-5x18-3ga | Rack Protector - 5 x 18 in, 3 Ga. | Fits 5 in post / 18 in H | warehouse-safety | Rack Protection | 55 | [5 empty] | PSE-FITS-5-IN-POST-18-IN-H | Create as draft
rack-protector-5x24-3ga | Rack Protector - 5 x 24 in, 3 Ga. | Fits 5 in post / 24 in H | warehouse-safety | Rack Protection | 70 | [5 empty] | PSE-FITS-5-IN-POST-24-IN-H | Create as draft
pallet-rack-guard-end-46x3x5 | Pallet Rack Guard End - 46 x 3 x 5 in | 46 x 3 x 5 in | warehouse-safety | Rack Protection | 205 | [5 empty] | PSE-46-X-3-X-5-IN | Create as draft
upright-protector-7x7x18 | Upright Protector - 7 x 7 x 18 in | 7 W x 7 D x 18 H in | warehouse-safety | Rack Protection | 55 | [5 empty] | PSE-7-W-X-7-D-X-18-H-IN | Create as draft
upright-protector-7x7x12 | Upright Protector - 7 x 7 x 12 in | 7 W x 7 D x 12 H in | warehouse-safety | Rack Protection | 45 | [5 empty] | PSE-7-W-X-7-D-X-12-H-IN | Create as draft
floor-angle-guard-warehouse-24x5x3 | Floor Angle Guard - Warehouse 24 in | 24 L x 5 H x 3 W in | warehouse-safety | Floor Guards | 100 | [5 empty] | PSE-24-L-X-5-H-X-3-W-IN | Create as draft
floor-angle-guard-warehouse-48x5x3 | Floor Angle Guard - Warehouse 48 in | 48 L x 5 H x 3 W in | warehouse-safety | Floor Guards | 140 | [5 empty] | PSE-48-L-X-5-H-X-3-W-IN | Create as draft
floor-angle-guard-warehouse-60x5x3 | Floor Angle Guard - Warehouse 60 in | 60 L x 5 H x 3 W in | warehouse-safety | Floor Guards | 190 | [5 empty] | PSE-60-L-X-5-H-X-3-W-IN | Create as draft
floor-angle-guard-warehouse-96x5x3 | Floor Angle Guard - Warehouse 96 in | 96 L x 5 H x 3 W in | warehouse-safety | Floor Guards | 300 | [5 empty] | PSE-96-L-X-5-H-X-3-W-IN | Create as draft
floor-angle-guard-warehouse-120x5x3 | Floor Angle Guard - Warehouse 120 in | 120 L x 5 H x 3 W in | warehouse-safety | Floor Guards | 360 | [5 empty] | PSE-120-L-X-5-H-X-3-W-IN | Create as draft
anti-theft-parking-bollard-collapsible | Anti-Theft Parking Bollard - Collapsible | Collapsible parking bollard | warehouse-safety | Parking Bollards | 306 | [5 empty] | PSE-COLLAPSIBLE-PARKING-BOLLARD | Create as draft

## Shopify Existing
Shopify Product ID | Current Title | Verified Model | Current Price | Available | Current SKU | Desired SKU | Title Check | Price Check
9193619980426 | PSE 420-1 | 420-1 | 852.91 | 4 |  | PSE-420-1 | Title matches | Price verification required
9193606971530 | PSE 33-8 | PSE 33-8 | 1042.74 | 6 |  | PSE-33-8 | Title matches | Price verification required
9193580757130 | PSE FWB | PSE FWB | 1141.9 | 3 |  | PSE-FWB | Title matches | Price verification required
9193579872394 | PSE 33-147-8-4 | PSE 33-147-8-4 | 1567.33 | 2 |  | PSE-33-147-8-4 | Title matches | Price verification required
9193579446410 | PSE 20-18 | PSE 20-18 | 1309.7 | 11 |  | PSE-20-18 | Title matches | Price verification required
9193578889354 | PSE 33-12 | PSE 33-18 | 1249.12 | 4 |  | PSE-33-18 | Title correction required | Price verification required
9193578594442 | PSE 20-12 | PSE 20-12 | 891.46 | 8 |  | PSE-20-12 | Title matches | Price verification required
9193578397834 | PSE 20-24 | PSE 20-24 | 1499.44 | 3 |  | PSE-20-24 | Title matches | Price verification required
9193578201226 | PSE 33-12 | PSE 33-12 | 1008.93 | 10 |  | PSE-33-12 | Title matches | Price verification required
9193566240906 | PSE 20-33-2 | PSE 20-33-2 | 501.62 | 5 |  | PSE-20-33-2 | Title matches | Price verification required
9193566208138 | PSE 100-20-8-18 | PSE 100-20-8-18 | 1484.28 | 4 |  | PSE-100-20-8-18 | Title matches | Price verification required
9193566175370 | PSE 20-33-6 | PSE 20-33-6 | 633.41 | 9 |  | PSE-20-33-6 | Title matches | Price verification required
9193566142602 | PSE 20-33-4 | PSE 20-33-4 | 548.49 | 7 |  | PSE-20-33-4 | Title matches | Price verification required

## Import Readiness
Gate | Requirement | Owner | Status | Evidence | Blocking
Data | 72 catalogue products mapped | Migration | Complete | Product Mapping sheet | Yes
Data | Existing Shopify IDs and stock preserved | Migration | Complete | Shopify Existing sheet | Yes
Data | All current Shopify prices reconciled | Migration | In progress | Price Difference column | Yes
Data | Every product/variant has a unique SKU | Migration | Pending | Desired SKU column | Yes
Media | Product, context, and brochure media mapped | Migration | Pending |  | Yes
Theme | Pixel-matched Liquid theme built as unpublished theme | Development | Pending |  | Yes
QA | Desktop, tablet, and mobile comparison passed | QA | Pending |  | Yes
Commerce | Cart, shipping, tax, and checkout test passed | Merchant + QA | Pending |  | Yes
Launch | Domain, redirects, analytics, and tracking approved | Merchant + Migration | Pending |  | Yes